## Bug
No | Description | Module | Status | By | Remark
1 | In check in screen, while customer is staying different than reserved day, Checkout is not asking for no of days exceed the days given | Lodge | Open |  | What will happen if leaving early? And if no of reservation days is not matching with no of days stayed, alert will be shown, but system should allow to check out… Reopen
2 | After checkout form is not refreshing | Lodge | Closed
3 | In Check in form, after generating invoice, immediately view invoice is throwing exception. | Lodge | Open
4 | Moveing folder is not happening in treeview in Navigator | Navigator | Open
5 | Check out time is not getting tracked | Lodge | Closed
6 | Checkin form-> new check in -> new reservation -> new customer... Customer file not added in navigator | Lodge | Open |  | Complex, least priority
7 | Attachment symbol is not showing in navigator when form is newly created and add attachment immediately. | Navigator | Open
8 | When checking out [Lodge].[CheckinUpdateCheckOut] is throwing error when it is being called from UpdateComplition() in Crystal.Activity.Component.Dao | Lodge | Closed
9 | Vanilla.Accontat.Facade.Invoice.LineItem.Server.cs -> public override BinAff.Facade.Library.Dto Convert(BinAff.Core.Data data) has thrown object reference not set to an reference error while loading old record | Check in | Open
10 | Alert for extra bed when reservation, check in, check out is happening. Apart from that assign extra bed information to DTO, by default extra bed will be as per definition in room. If no extrabed, it has to be made 0. | Check in | Open |  | Retinue.Lodge.WinForm.CheckInForm.SaveBefore() Comment is written
11 | Validate number of bed not more than available beds | Check in | Open |  | Retinue.Lodge.WinForm.CheckInForm.ValidateForm() Comment is written
12 | Calculate extra bed in invoice generation | Check in | Open
13 | If checkin is done, while deleting reservation the message will be shown like "Unable to delete. Following Room checkin has this dependency: Room has reservation from 25-05-2015 till 26-05-2015". Checkin file name should be shown and the text will be "...Room is checked in for 25-05-2015 to 26-05-2015" | Navigator | Open
14 | In Navigator, while deleting payment, if there is any dependency, it is showing deniel message, but not showing the depended file. | Navigator | Open
15 | If attachement is deleted in form it is not reflecting in Navigator attachment icon | Navigator | Open
16 | While deleting payment, it isnot checking that it is linked with any file or not. | Payment | Open
17 | Open any form -> click pick ancestor -> in list view of open dialogue add one folder and name something ->-> This will create listview node in Navigator properly, but in treeview it will be shown as new folder. | Register | Open
18 | Deleting from form container, is not deleting from navigator | Form Container / Register | Open
19 | Add one payment as cash -> Click edit in line item grid -> click on edit button -> Showing error | Payment | Open

## Feature
No | Description | Module | Status | By | Remark
1 | Refresh | Navigator | Open
2 | Megre folders if same name found while pasting a folder | Navigator | Open
3 | Open in new Tab | Navigator |  |  | ?
4 | Personalization of folder (Sort, View) | Navigator
5 | Multiple Payment for one invoice | Invoice | Open
6 | Revert check out in case of operator mistake | Checkin | Open
7 | Recycle bin | Navigator and all component | Open
8 | Automatic report generation | Report | Open