## Bug
No | Description | Module | Status | By | Remark
1 | Moveing folder is not happening in treeview in Navigator | Navigator | Open
2 | Checkin form-> new check in -> new reservation -> new customer... Customer file not added in navigator | Lodge | Open |  | Complex, least priority
3 | Attachment symbol is not showing in navigator when form is newly created and add attachment immediately. | Navigator | Open
4 | Vanilla.Accontat.Facade.Invoice.LineItem.Server.cs -> public override BinAff.Facade.Library.Dto Convert(BinAff.Core.Data data) has thrown object reference not set to an reference error while loading old record | Check in | Open
5 | Alert for extra bed when reservation, check in, check out is happening. Apart from that assign extra bed information to DTO, by default extra bed will be as per definition in room. If no extrabed, it has to be made 0. | Check in | Open | Arpan | Retinue.Lodge.WinForm.CheckInForm.SaveBefore() Comment is written
6 | Validate number of bed not more than available beds | Check in | Open |  | Retinue.Lodge.WinForm.CheckInForm.ValidateForm() Comment is written
7 | Calculate extra bed in invoice generation | Check in | Open
8 | If checkin is done, while deleting reservation the message will be shown like "Unable to delete. Following Room checkin has this dependency: Room has reservation from 25-05-2015 till 26-05-2015". Checkin file name should be shown and the text will be "...Room is checked in for 25-05-2015 to 26-05-2015" | Navigator | Open
9 | In Navigator, while deleting payment, if there is any dependency, it is showing deniel message, but not showing the depended file. | Navigator | Open
10 | If attachement is deleted in form it is not reflecting in Navigator attachment icon | Navigator | Open
11 | While deleting payment, it isnot checking that it is linked with any file or not. | Payment | Open
12 | Open any form -> click pick ancestor -> in list view of open dialogue add one folder and name something ->-> This will create listview node in Navigator properly, but in treeview it will be shown as new folder. | Register | Open
13 | Deleting from form container, is not deleting from navigator | Form Container / Register | Open
14 | Add one payment as cash -> Click edit in line item grid -> click on edit button -> Showing error | Payment | Open
15 | When attachment form is deleted, the link with depended for in not getting deleted. As for example, in Reservation add advance payment -> Delete payment form from navigator -> in attachment list of reservation form one item will be shown with .frm path | Not sure about impact | Open
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Feature
No | Description | Module | Status | By | Remark
1 | Refresh | Navigator | Open
2 | Megre folders if same name found while pasting a folder | Navigator | Open
3 | Open in new Tab | Navigator |  |  | ?
4 | Personalization of folder (Sort, View) | Navigator
5 | Multiple Payment for one invoice | Invoice | Open
6 | Revert check out in case of operator mistake | Checkin | Open
7 | Recycle bin | Navigator and all component | Open
8 | Automatic report generation | Report | Open